## Sheet1
Week | Tasks | Difficulty
2021-04-10 | Create spreadsheet of project plan | Easy
| Create trello board | Easy
| Create Git repo | Easy
2021-04-16 | Replace the scaffolding code with the flask code | Medium
| Ensure the app runs locally without errors | Medium
| Ensure the app runs in Cloud Shell without errors | Medium
2021-04-23 | Set up GitHub Actions | Hard
| Add the GitHub Actions badge to the README | Medium
| Create the App Service in Azure | Medium
| Test the app running in Azure App Service | Medium
2021-05-02 | Set up the Azure DevOps pipeline | Hard
2021-05-05 | Create architectural diagram | Medium
| Take screenshots demonstrating key steps | Easy
| Create README file with full instructions of how to run the code | Medium
2021-05-16 | Create demo video and post to YouTube | Medium
Goals
Submit project
Q4 plan | Submit the project
Yearly plan | Review the code and ensure it still works